## Gantt
multimodal-bio-fusion ¦ Research Project Plan
As of October 19, 2026. Fall weeks start Monday; January to March 2027 is a monthly horizon. The research plan comes first (17, 18, 24, 41, 44, 42); Coupled Mamba and cross-attention (20, 21, 25) follow from January.
██ = scheduled work ◆ = milestone Conditional = candidate work, subject to scope and feasibility.
Dates are inclusive. Details lists expected outputs. |  |  |  |  | September 2026 |  |  |  | October 2026 |  |  |  | November 2026 |  |  |  |  | December 2026 |  |  |  | 2027
ID | Task / research outcome | Status | Start | End | 9/7 | 9/14 | 9/21 | 9/28 | 10/5 | 10/12 | 10/19 | 10/26 | 11/2 | 11/9 | 11/16 | 11/23 | 11/30 | 12/7 | 12/14 | 12/21 | 12/28 | Jan | Feb | Mar
Stages 1 and 2: representation analysis and defining alignment
1 | Initial six-paper review | Complete | Sep 7 | Sep 21 | ██ | ██ | ██
2 | Continue paper synthesis and notebook walkthrough | In progress | Sep 21 | Oct 7 |  |  | ██ | ██ | ██
3 | Check label meaning, sequence regions and duplicates | In progress | Sep 21 | Oct 7 |  |  | ██ | ██ | ██
4 | Check train/test separation and preprocessing | Complete | Sep 21 | Oct 3 |  |  | ██ | ██
5 | Trace runs, seeds and reproducibility evidence | Complete | Sep 21 | Oct 3 |  |  | ██ | ██
6 | Interpret representation metrics and pilot findings | Complete | Sep 21 | Oct 3 |  |  | ██ | ██
7 | Draft an operational definition of alignment | In progress | Sep 21 | Oct 7 |  |  | ██ | ██ | ██
8 | Map BioLangFusion and IsoFormer inputs, including DNA | Complete | Sep 28 | Oct 2 |  |  |  | ██
9 | Run published-split comparisons for both datasets | Complete | Oct 1 | Oct 3 |  |  |  | ██
10 | Draft Stage 1 methods and findings in Overleaf | In progress | Sep 26 | Oct 7 |  |  | ██ | ██ | ██
11 | Clarify the lab tokenizer and benchmark opportunity | Planned | Sep 28 | Oct 5 |  |  |  | ██ | ██
12 | Prepare the Oct 7 evidence and question set | In progress | Oct 1 | Oct 6 |  |  |  | ██ | ██
13 | Oct 7 review and working alignment definition | Planned | Oct 7 | Oct 7 |  |  |  |  | ◆
14 | Revise Stage 1 claims, figures and methods | Planned | Oct 8 | Oct 11 |  |  |  |  | ██
15 | Specify the first matched comparison protocol | Planned | Oct 8 | Oct 11 |  |  |  |  | ██
Stages 3 and 4: fusion experiments and evaluation
16 | Harden single-model and simple-fusion baselines | In progress | Oct 6 | Oct 11 |  |  |  |  | ██
17 | Run matched BioLangFusion-style comparisons; reproduce BioLangFusion exactly on its five published datasets (plan item 1, Phase A) | In progress | Oct 12 | Oct 25 | [5 empty] | ██ | ██
18 | Repeat diagnostics and null/control comparisons, including the mRFP synonymous control (plan item 5) | Planned | Oct 12 | Oct 18 | [5 empty] | ██
19 | Interpret baseline findings and revise the next experiment | Planned | Oct 19 | Oct 25 | [6 empty] | ██
20 | Prepare Coupled Mamba inputs and feasibility tests, after the research plan's baselines and datasets | Planned | Jan 4 | Jan 17 | [17 empty] | ██
21 | Evaluate Coupled Mamba against the research plan's baselines on its datasets | Planned | Jan 18 | Feb 7 | [17 empty] | ██ | ██
22 | Candidate layer and PCA/variance comparisons | Conditional | Oct 19 | Nov 1 | [6 empty] | ██ | ██
23 | Candidate alignment-objective ablation | Conditional | Feb 8 | Feb 21 | [18 empty] | ██
24 | Additional DNA, RNA and protein encoder comparison: encoder swaps in the reproduced BioLangFusion pipeline (plan item 1, Phase B) | Planned | Oct 26 | Nov 8 | [7 empty] | ██ | ██
25 | IsoFormer-style cross-attention fusion with the Stage 1 encoders, after Coupled Mamba | Planned | Feb 8 | Feb 28 | [18 empty] | ██
26 | Agree tokenizer benchmark feasibility and protocol | Conditional | Oct 6 | Oct 18 |  |  |  |  | ██ | ██
27 | Candidate lab-tokenizer benchmark pilot | Conditional | Nov 2 | Nov 15 | [8 empty] | ██ | ██
28 | Repeat runs, quantify uncertainty and revise claims | In progress | Oct 12 | Nov 22 | [5 empty] | ██ | ██ | ██ | ██ | ██ | ██
29 | Synthesize evidence, limitations and next decisions | Planned | Nov 16 | Nov 29 | [10 empty] | ██ | ██
41 | LucaOne frozen baseline on stability and GTEx, matched comparison (plan item 2) | In progress | Nov 9 | Nov 22 | [9 empty] | ██ | ██
42 | mRNABench half-life (plan item 3) and translation efficiency (plan item 4) after the sequence and label gates | Planned | Nov 23 | Dec 20 | [11 empty] | ██ | ██ | ██ | ██
43 | Multi-teacher distillation, six DNA, five RNA and four protein teachers (plan item 7) | Conditional | Mar 1 | Mar 31 | [19 empty] | ██
44 | IsoFormer's cross-attention aggregator reproduced on GTEx as a baseline, beside LucaOne (not on the plan's list) | In progress | Nov 9 | Nov 22 | [9 empty] | ██ | ██
Research writing and coordination
30 | Research coordination and decision review | In progress | Sep 14 | Mar 31 |  | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██
32 | Maintain and revise the living Overleaf manuscript | In progress | Sep 26 | Mar 31 |  |  | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██
CAP6942 course deliverables
33 | Bibliography, Research Canvas and project plan | In progress | Sep 26 | Sep 27 |  |  | ██
34 | Prepare final course report, presentation and video | Planned | Nov 16 | Dec 6 | [10 empty] | ██ | ██ | ██
35 | Course rehearsal checkpoint | Planned | Dec 1 | Dec 1 | [12 empty] | ◆
36 | Final course report checkpoint | Planned | Dec 7 | Dec 7 | [13 empty] | ◆
37 | Course presentation and video checkpoint | Planned | Dec 8 | Dec 8 | [13 empty] | ◆
Research continuation
38 | Further experiments and external validation | Conditional | Mar 1 | Mar 31 | [19 empty] | ██
39 | Consolidate manuscript and review publication readiness | Planned | Feb 1 | Mar 31 | [18 empty] | ██ | ██
40 | March research review and next-step decision | Planned | Mar 31 | Mar 31 | [19 empty] | ◆
Update the dates and corresponding week cells together. This workbook is a schedule snapshot; dates do not automatically move the bars.

## Details
Expected outputs and dependencies
IDs match the Gantt. Dependencies refer to the outputs needed before a later task can be completed.
ID | Task / research outcome | Expected output / review condition | Prerequisite IDs
Stages 1 and 2: representation analysis and defining alignment
1 | Initial six-paper review | Complete the initial six-paper review and retain paper notes for continued interpretation and discussion. | —
2 | Continue paper synthesis and notebook walkthrough | Explain biological inputs, frozen encoders, pooling, probes and metrics; connect each retained result to the relevant paper and its limitations. | —
3 | Check label meaning, sequence regions and duplicates | Record assay/target provenance, retained rows, sequence regions, duplicates and translation assumptions before drawing biological conclusions. | —
4 | Check train/test separation and preprocessing | Identify evaluation unit; check whether duplicate or related sequences cross train/test boundaries and whether fitted preprocessing uses training data only. Document what the split can support. | —
5 | Trace runs, seeds and reproducibility evidence | Link selected outputs to notebook, data, model revisions, environment, split and seed settings. Compare reruns and investigate differences in results. | —
6 | Interpret representation metrics and pilot findings | Explain what CKA, neighborhood, CCA/retrieval and predictive probes measure; distinguish observations from explanations. Prepare PCA/variance and layer-choice questions for Mina. | —
7 | Draft an operational definition of alignment | Define objects being related, biological correspondence versus representation similarity, sample/position unit, metric, reference or null, and permitted conclusions. Keep useful fusion as a separate test. | —
8 | Map BioLangFusion and IsoFormer inputs, including DNA | Compare paper and local checkpoints, tokenization, sequence regions, codon mapping, pooling, labels, splits and metrics for BioLangFusion (CodonBERT stability data) and IsoFormer (GTEx data with genomic DNA). Done October 2: the GTEx pilot (2,000 transcripts with 6,000-nucleotide DNA windows) and its registry entry give each encoder its own input. | —
9 | Run published-split comparisons for both datasets | Done October 3 in Stage1_analysis.ipynb: probes fit on rows sampled from BioLangFusion's published stability split and IsoFormer's GTEx split, scored on their test splits, with each paper's encoder combinations. Trained fusion heads remain Stage 3 work. | 8
10 | Draft Stage 1 methods and findings in Overleaf | Join Mina’s project, draft Stage 1 background/methods, attach supported figures and annotate unresolved claims. This is the first writing increment of the living manuscript. | —
11 | Clarify the lab tokenizer and benchmark opportunity | Ask Julian for the exact group, tokenizer/paper and intended benchmark task. Establish inputs, access, comparison unit and collaborators before promising a shared experiment. | —
12 | Prepare the Oct 7 evidence and question set | Assemble the explainable pipeline, source-linked findings, unresolved results, BioLangFusion pilot status and alignment-definition proposal. Distinguish established evidence from open hypotheses. | —
13 | Oct 7 review and working alignment definition | Review evidence with Mina and agree a working definition of alignment, its measurements and limits, and the next comparison. Record remaining questions and required revisions. | 2, 3, 4, 5, 6, 7, 9, 10, 12
14 | Revise Stage 1 claims, figures and methods | Incorporate Mina’s feedback in the notebook explanations and manuscript; correct unsupported interpretations and identify specific reruns or experiments needed. | 13
15 | Specify the first matched comparison protocol | Set biological question, target, evaluation unit, data exclusions, checkpoints, preprocessing, metrics, seeds, tuning budget and success/stop criteria. The research plan's baselines come first; Coupled Mamba remains the project's first design after them. Details follow the review. | 13
Stages 3 and 4: fusion experiments and evaluation
16 | Harden single-model and simple-fusion baselines | Prepare comparable single-encoder and concatenation + MLP predictors, input tests and controlled configurations. Keep the original linear concatenation probe distinct. Final comparisons use protocol 15. | 13
17 | Run matched BioLangFusion-style comparisons; reproduce BioLangFusion exactly on its five published datasets (plan item 1, Phase A) | Compare selected paper-inspired fusion methods and unimodal baselines on the same evaluation data, with adaptations and resources reported. Widened by the research plan: reproduce BioLangFusion exactly (its encoders, codon grid, three heads, TextCNN, published splits and recipe) on Fungal, E. coli, mRNA stability, Ab1 and CoV-Vac, recording every unreported detail as a deviation; this is the matched baseline for 21. Preserve null or negative results. | 9, 15, 16
18 | Repeat diagnostics and null/control comparisons, including the mRFP synonymous control (plan item 5) | Check label/feature controls, synonymous-input behavior and representation diagnostics under the agreed evaluation. Test whether the claimed signal survives the relevant nulls. Includes, in parallel, the mRFP synonymous control with cached embeddings: nucleotide encoders against GC3, codon-use and structure proxies; protein encoders as the invariant negative control. | 14, 15, 16
19 | Interpret baseline findings and revise the next experiment | Compare effect sizes, variation and failure cases; distinguish geometry from predictive complementarity. Revise the question and manuscript before choosing additional complexity. | 17, 18
20 | Prepare Coupled Mamba inputs and feasibility tests, after the research plan's baselines and datasets | Implement the project's first design with explicit sequence/feature correspondence; test dimensions, controlled cases and resource feasibility once the research plan's baselines (17, 24, 41, 44) and datasets (42) are in place. | 17, 24, 41, 42, 44
21 | Evaluate Coupled Mamba against the research plan's baselines on its datasets | Compare predictive performance, uncertainty, runtime and memory under the matched evaluation protocol. Score it against every research plan baseline (reproduced heads, encoder swaps, LucaOne, IsoFormer) on every dataset of the plan, including half-life and translation efficiency (42). Interpret gains, losses or unchanged performance. | 19, 20, 24, 41, 42, 44
22 | Candidate layer and PCA/variance comparisons | After choosing the relevant encoder/layer question, compare selected representations or variance subspaces. Fit any reduction within training data and separate using an earlier layer from truncating or retraining a model. The representation-level comparison of top-10 principal components and the rest is complete in Stage 1. | 18
23 | Candidate alignment-objective ablation | If selected, compare the same fusion setup with and without the specified alignment objective under matched tuning. The pilot’s alignment/error association is not evidence that the loss must help or hurt. | 21
24 | Additional DNA, RNA and protein encoder comparison: encoder swaps in the reproduced BioLangFusion pipeline (plan item 1, Phase B) | Keep the reproduced BioLangFusion splits, grid, heads, TextCNN and evaluation fixed; replace one encoder at a time (CaLM or other suitable codon models, mRNA-FM, ProtBERT, other DNA encoders; ESM-2 150M as a further protein candidate), then promising triples, on Fungal, E. coli, mRNA stability and Ab1 (CoV-Vac if feasible). Runs directly after the reproduction (17) and before LucaOne (41), in the plan's implementation order. Report published, reproduced, best single, each head, each swap and Δfusion with seeds and paired differences. Now planned rather than conditional; the cleanest test of H2. | 17, 19
25 | IsoFormer-style cross-attention fusion with the Stage 1 encoders, after Coupled Mamba | The project's second design, after Coupled Mamba: cross-attention with the encoders Stage 1 points to, on GTEx and as the competitor on coding sequence, scored against the same baselines, including IsoFormer's own aggregator (44). Report relevant differences from IsoFormer’s fine-tuning regime. | 21, 44
26 | Agree tokenizer benchmark feasibility and protocol | With the identified lab group, agree a shared task, data, tokenizer version, access and fair comparison protocol. | 11, 13
27 | Candidate lab-tokenizer benchmark pilot | Run only after collaborators agree scope and access and a matched protocol exists. Keep tokenizer effects separate from model capacity, training data and downstream evaluation differences. | 26
28 | Repeat runs, quantify uncertainty and revise claims | Repeat selected configurations as results arrive; investigate variation, leakage or contradictory findings, and revise claims. This spans the experiment cycle rather than following implementation as a single final check. | 15, 16
29 | Synthesize evidence, limitations and next decisions | Build a comparison table with sources/runs, uncertainty, resource costs, negative findings and scope limits. Review which conclusions are supported and which further experiments are justified. | 19, 24, 41, 44
41 | LucaOne frozen baseline on stability and GTEx, matched comparison (plan item 2) | Verify LucaOne's input limits (1,280 tokens) and sequence types against the stability and GTEx files; extract frozen embeddings on the same folds and head as the fusion models; compare against the best single encoder and the best fused model; report cost and truncation. After the encoder swaps (24), in the plan's implementation order. | 16, 17, 24
42 | mRNABench half-life (plan item 3) and translation efficiency (plan item 4) after the sequence and label gates | Plan items 3 and 4, each target run separately. Gates first: 5' and 3' UTRs and coding-sequence coordinates present, labels and species present, grouped non-leaking splits; half-life, translation efficiency and ribosome load kept as separate targets. Half-life: CDS only, CDS + 3' UTR, full transcript, and + protein. Translation efficiency: 5' UTR, CDS, full transcript, + protein, and the three-encoder fusion, with RiboNN as the external benchmark. Gain over the best full-transcript baseline. After the plan's baselines (24, 41, 44) and before the project's designs (20, 21), so every baseline is scored on these tasks. | 17, 24, 41
43 | Multi-teacher distillation, six DNA, five RNA and four protein teachers (plan item 7) | In March, after the core comparisons and the project's designs, as the research plan states. Teachers: the twelve Stage 1 encoders plus two DNA and one RNA encoder, chosen with Mina. The plan's relational objective (each teacher's cosine-similarity matrix matched through its own projection, equal weights until the uniform baseline is evaluated); RNA first as in the plan's worked example, then DNA and protein; the composition-controlled target reported beside the raw one. Evaluate each student, then fuse the three; report Δstudent and Δteacher with cost on the five BioLangFusion benchmarks with the reproduced heads. | 21, 25, 29
44 | IsoFormer's cross-attention aggregator reproduced on GTEx as a baseline, beside LucaOne (not on the plan's list) | Not on the research plan's list, but the published distinct-molecule baseline: IsoFormer's cross-attention aggregator with frozen Nucleotide Transformer v2 (DNA window), each RNA encoder in the transcript role and ESM-2 150M (protein), on the GTEx pilot and then the full table; R² and Spearman averaged over tissues as IsoFormer reports them, with the four length features beside it. Runs beside LucaOne (41), before the project's designs. | 8, 9, 16
Research writing and coordination
30 | Research coordination and decision review | Maintain the questions, decisions and follow-ups from regular team and advisor discussions. Confirm future meeting dates with Mina. | —
32 | Maintain and revise the living Overleaf manuscript | Update methods, figures, claims, citations and open questions as research changes. Writing begins with Stage 1 and continues through review, new experiments and later consolidation. | —
CAP6942 course deliverables
33 | Bibliography, Research Canvas and project plan | Submit the annotated bibliography and Research Canvas for Team Assignment 1, and the research project plan for Team Assignment 2. Both are due September 27 at 23:59 Eastern. | —
34 | Prepare final course report, presentation and video | Adapt the evolving manuscript and evidence to the course report, presentation and video requirements. Rehearse explanations and incorporate teammate and advisor feedback. | —
35 | Course rehearsal checkpoint | Rehearse the scientific account and record corrections; confirm the course’s exact instructions in WebCourses. | —
36 | Final course report checkpoint | Review evidence, attribution and AI disclosure; confirm and complete the required course submission. | 34, 35
37 | Course presentation and video checkpoint | Deliver the course presentation/video using the reviewed evidence and acknowledged limitations. | 34, 35
Research continuation
38 | Further experiments and external validation | Select and run extensions justified by the reviewed evidence, biological relevance, collaborators and available resources. In March, after the project's designs. Includes the optional structure extension (plan item 6): sequence against sequence plus predicted structure features, only on tasks where structure plausibly acts. | 21, 25, 29
39 | Consolidate manuscript and review publication readiness | Refine the manuscript already underway, integrate additional evidence and seek group feedback. Venue, submission date and final research end remain undecided. | —
40 | March research review and next-step decision | Review the evidence and decide whether to extend the experiments, revise the manuscript, prepare a submission or change direction. Adjust the timeline to the chosen next steps. | 39
Planning notes
Update the dates and corresponding week cells together in Gantt. Keep each task ID unchanged when editing its expected output or prerequisites.
The team completed the initial six-paper review by September 21. Continued interpretation and discussion run through the October 7 meeting. September 21 start dates for current work are approximate planning anchors.
October 7 is the review with Mina and the target for a working alignment definition. Stage 1 includes the immediate revisions after that meeting. Future experiment dates are proposed windows.
The research plan's items come first: its baselines (17, 24, 41, with IsoFormer as 44), the mRFP control (18) and its datasets (42). Coupled Mamba (20, 21) and IsoFormer-style cross-attention (25) follow from January and are scored against all of them. Optional layer/PCA and alignment-loss comparisons depend on earlier findings and available capacity. The tokenizer and collaborating group must first be identified with Julian.
The bibliography, Research Canvas and project plan are due September 27 at 23:59 Eastern. December 1, 7 and 8 checkpoints come from the course schedule; confirm the corresponding WebCourses deadlines.
AI supports implementation, paper discussion, analysis and writing throughout the project. Each research task includes interpreting its evidence and revising the resulting claims. OpenAI Codex organized the original plan; Claude assisted with the September 29 revision adding the DNA modality, the October 3 status update and the October revisions that fold in Mina's research plan.
Coordination began September 14. Stage 1 manuscript drafting begins September 26 and continues in Overleaf as the work develops. March is a planning horizon rather than a fixed research endpoint.
Planning example: Mélot-Chesnel, Designing Trustworthy Generative AI Agents for Collaborative Decision Making (2026), section 4 and Figure 1, explicitly schedules reconsidering questions and hypotheses between studies. This informed retaining time for interpretation and revision. https://doi.org/10.3233/FAIA260562
Planning example: UQ AGRC7617, Sequential mid-project assessment, uses a proposal and Gantt with supervisor discussion, followed by AI feedback on mature drafts. This illustrates review within planning. https://course-profiles.uq.edu.au/course-profiles/AGRC7617-62151-7660
These examples informed the September 27 planning discussion. They do not establish CAP6942 requirements or measured AI time savings.